## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
spRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | REspONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | customer | register myself with valid email id | I Can Receive A Confirmation/Verification Mail | 1
2 | SB1/US2 | customer | Login Into The app | to place in order and manage profile | 1
3 | SB1/US3 | customer | forgot password | to reset the previous password if its lost | 1
4 | SB1/US4 | customer | create new account | to choose from different services | 1
5 | SB1/US5 | customer | Modify The Account Password | I Can Keep My Account Secure | 1
6 | SB1/US6 | customer | view all subscription available | to opt from different services | 1
7 | SB2/US7 | customer | view order history | previous completed and future order transition list | 1
8 | SB3/US8 | customer | Can set vacation day off | to stop a delivery attempt | 1
9 | SB1/US9 | customer | view wallet balance | to view amount of money stored in the wallet | 1
10 | SB1/US10 | customer | track expense | I Can Analyze My expenditure | 1
11 | SB2/US11 | customer | track transaction | to track current order status | 1
12 | SB3/US12 | customer | contact customer support | so that I get get required help on my issue | 1
13 | SB1/US13 | customer | new order placed | so that I could enjoy the service | 1
14 | SB1/US14 | customer | add item to cart | so that I don’t want to checkout on every item | 1
15 | SB1/US15 | customer | delete item from cart | to remove item which I don’t required | 1
16 | SB1/US16 | customer | finalize the cart | to proceed to paymant gateway | 1
17 | SB1/US17 | customer | subscribe an item | to aviod daily ordering the product | 1
18 | SB1/US18 | customer | view details | I Can be updated about product details | 1
19 | SB3/US19 | customer | see available offers | so that I can save money | 1
20 | SB1/US20 | customer | choose offer | to apply promo code or offer on final cart | 1
21 | SB1/US21 | customer | special instructions | to precisely product delivery with customers convience | 1
22 | SB1/US22 | customer | add address | I tell where to deliver order | 1
23 | SB1/US23 | customer | save address | to confirm new address | 1
24 | SB1/US24 | customer | view paymant method | to see the what paymant options are available | 1
25 | SB1/US25 | customer | chooose available paymant method | to proceed to paymant gateway | 1
26 | SB1/US26 | customer | place order | To confirm the order | 1
27 | SB1/US27 | customer | order confirmed | I could know money is succesfully deducted | 1
28 | SB1/US28 | owner | order accepted | order can be processed | 2
29 | SB1/US29 | delivery man | track order | to check list of order which are delivered or to be delivered | 3
30 | SB1/US30 | owner | order detail | to see details of every order | 2
31 | SB1/US31 | owner | to see customer record | so to analyse and use it in other services like suggestion or track behaviour | 2
32 | SB1/US32 | owner | items availability | to add or removes stock | 2
33 | SB1/US33 | owner | delivery man details | to have list and quality of service of employess | 2
34 | SB1/US34 | customer | delivery man details | to contact the for accurate delivery and to avoid chaos | 1
35 | SB1/US35 | delivery man | have customers location | I could deliver the order | 3
36 | SB1/US36 | delivert man | have customers contact no. | so I could take help for directions as well to deliver to product | 3
37 | SB1/US37 | delivery man | Delete order for incomplete transition or issue | to proceed the refund and complete the furthers orders | 3
38 | SB1/US38 | delivert man | View order list for all customers to deliver item | to check the bills of indivisual customers | 3
39 | SB1/US39 | delivery man | acknowledge delivery | to get confirmation order is delivery to right customer | 3
40 | SB1/US40 | delivert man | check total deliveries | to keep daily records so to maintain daily target | 3
41 | SB1/US41 | delivert man | to check special instructions like delivery time,urgent delivery etc | so make customer satisfy | 3
42 | SB1/US42 | owner | contact customer for non availabilty of products | to maintain customer and client relationship | 2
43 | SB1/US43 | customer | customer feedback | to get customer feedback | 3
44 | SB1/US44 | delivery man | Deliveryman feedback | to get delivery feedback | 3
45 | SB1/US45 | customer | Product ratings | to get product ratings | 3
46 | SB1/US46 | customer | Update address | to update delivery address | 1
47 | SB1/US47 | customer | Cancel order | to cancel already placed order | 1
48 | SB1/US48 | customer | enter offer code | to get the offers | 3
49 | SB1/US49 | customer | products suggestion | to suggest product to users | 3
50 | SB1/US50 | owner | mark item as out of stock | to temove out of stock item | 2
51 | SB1/US51 | owner | add new item | to add new item | 1
52 | SB1/US52 | owner | delete item | to delete an item | 2
53 | SB1/US53 | customer | update mobile no. | to update customer info. | 1
54 | SB1/ | owner | conformation mail on mail id | to acknowledge that they are successfully registered | 1
55 | SB4/US | owner | Apply encryption techniques | to make platform secure | 3
56 | SB4/US | owner | Testing the app | to test the app | 3
57 | SB4/US | owner | Applying payment gateway | to make payment of items | 3
58 | SB4/US | owner | Data transfer security | for secure data transmission | 3
59 | SB4/US | owner | Reverse Engineering | to find out the vulnerability | 3

## SprintBacklog 1
spRINT BACKLOG 1
US ID | USER STORY | TArm ID | TArmS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TArm COMPLETION
spRINT 1 - <Digital College>
SB1/US1 | register myself with valid email id | SB1/D1/T1 | create registration UI
|  | SB1/D1/T2 | Validation of the details
|  | SB1/D1/T3 | Connect registration page with server
|  | SB1/D1/T4 | Upload user details to server and store in database
|  | SB1/D1/T5 | revert user if successfully register.
|  | SB1/D1/T6 | Send Mail to user on succesfull registration
SB1/US2 | Login into app | SB1/D2/T1 | UI of the login screen
|  | SB1/D2/T2 | Validation of the details
|  | SB1/D2/T3 | Connect login page with server
|  | SB1/D2/T4 | Verify login details on server
|  | SB1/D2/T5 | Revert user if successfully verified
SB1/US3 | forgot password | SB1/D3/T1 | Click on forgot password button
|  | SB1/D3/T2 | Create UI for OTP request
|  | SB1/D3/T3 | Enter OTP on screen
|  | SB1/D3/T4 | Verify OTP
SB1/US5 | Modify The Account Password | SB1/D4/T1 | Click on change password
|  | SB1/D4/T2 | Enter old password
|  | SB1/D4/T3 | Enter new password
|  | SB1/D4/T4 | Password changed succesfully
SB1/US6 | view all subscription available | SB1/D5/T1 | View subscriptions
|  | SB1/D5/T2 | Choose subscriptions
|  | SB1/D5/T3 | Apply subscriptions
|  | SB1/D5/T4 | See discount applied
SB1/US27 | Choose available items | SB1/D6/T1 | See list of items
|  | SB1/D6/T2 | Choose Items
|  | SB1/D6/T3 | Add items to cart
|  | SB1/D6/T4 | Finalize the cart
SB1/US7 | view order history | SB1/D7/T1 | create UI to view order history
|  | SB1/D7/T2 | Fetch order history from server
|  | SB1/D7/T3 | Filter order history according to month
SB1/US150 | Can set vacation day off | SB1/D8/T1 | create UI to set vacation time off
|  | SB1/D8/T2 | select days for which you have to set off
|  | SB1/D8/T3 | Send details to server
|  | SB1/D8/T4 | Acknowledge user that vacation set off has been done
SB1/US28 | view wallet balance | SB1/D9/T1 | Create UI to show wallet balance
|  | SB1/D9/T2 | fetch available balance from server
|  | SB1/D9/T3 | Show balance on the user screen after fetching
|  | SB1/D9/T4 | update balance after subscription to particular item
SB1/US50 | track expense | SB1/D10/T1 | Create UI for track expense section
|  | SB1/D10/T2 | show average expenditure on monthly basis
|  | SB1/D10/T3 | show expenditure according to specific subscription
|  | SB1/D10/T4 | update average expense after subscription to particular item
SB1/US53 | track transaction | SB1/D11/T1 | UI screen for track transaction page
|  | SB1/D11/T2 | fetch transaction record from server for that particular user
|  | SB1/D11/T3 | Filter transaction record according to month
|  | SB1/D11/T4 | check transaction status

## SB Hours 01
sprint Backlog 1
S. No. | User Story | Tarms | T M | Status | Days Left in sprint
Hours
EPIC-III : Final Deployment Of Project
1 | register myself with valid email id | create registration UI
Validation of the details
Connect registration page with server
Upload user details to server and store in database
revert user if successfully register.
Send Mail to user on succesfull registration
2 | Login into app | UI of the login screen
Validation of the details
Connect login page with server
Verify login details on server
Revert user if successfully verified
3 | forgot password | Click on forgot password button
Create UI for OTP request
Enter OTP on screen
Verify OTP
4 | Modify The Account Password | Click on change password
Enter old password
Enter new password
Password changed succesfully
5 | view all subscription available | View subscriptions
Choose subscriptions
Apply subscriptions
See discount applied
6 | Choose available items | See list of items
Choose Items
Add items to cart
Finalize the cart
7 | view order history | create UI to view order history
Fetch order history from server
Filter order history according to month
8 | Can set vacation day off | create UI to set vacation time off
select days for which you have to set off
Send details to server
Acknowledge user that vacation set off has been done
9 | view wallet balance | Create UI to show wallet balance
fetch available balance from server
Show balance on the user screen after fetching
update balance after subscription to particular item
10 | track expense | Create UI for track expense section
show average expenditure on monthly basis
show expenditure according to specific subscription
update average expense after subscription to particular item
11 | track transaction | UI screen for track transaction page
fetch transaction record from server for that particular user
Filter transaction record according to month
check transaction status
Verified By:
(Product Owner)

## SB BD Ch01
spring Backlog 01 burn down chart
Date | Planned Total Tarm | Actual Incompleted Tarm
2018-09-04 | 46 | 46 | Tarms
2018-09-06 | 41
2018-09-08 | 35
2018-09-16 | 28
2018-09-17 | 21
2018-09-20 | 15
Days

## SprintBacklog 2
VMRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
VMRINT 2 - <Digital College>
| Order Deatil | SB2/D1/T1 | Check order detail | VM+RV
|  | SB2/D1/T2 | Location of order | TG+RP
|  | SB2/D1/T3 | Is the order Valid | TG+VM+PC+SK
| Order Accepted | SB2/D2/T1 | Get the request | PC
|  | SB2/D2/T2 | Check if item available | SK+RV
|  | SB2/D2/T3 | Revert back with reVMonse | VM
|  | SB2/D2/T4 | Finalise the order | TG+RP
| To see customer record | SB2/D3/T1 | See the Customer info | PC+RV
|  | SB2/D3/T2 | Order placed by customer | VM
|  | SB2/D3/T3 | No. of total customers | TG+RP
|  | SB2/D3/T4 | No of orders placed | TG+VM+PC+SK
| Items Availability | SB2/D4/T1 | When order is placed a request is geneTGted | PC
|  | SB2/D4/T2 | GeneTGted request comes to owner portal | SK
|  | SB2/D4/T3 | Validating the order if items available | VM+RV
|  | SB2/D4/T4 | If item not available tell the user | TG+RP
|  | SB2/D4/T5 | When available flag the user about availability | TG+VM+PC+SK
| Deliver Men Details | SB2/D5/T1 | Know deliveSKen background details | PC
|  | SB2/D5/T2 | Gives credentials to delivery men | VM
|  | SB2/D5/T3 | Items he/she need to deliver | TG+RP
|  | SB2/D5/T4 | Address where they need to deliver | TG+VM+PC+SK
| Contact customer for non-availability of products | SB2/D6/T1 | When order is placed check for product | PC
|  | SB2/D6/T2 | if item not available tell the user | SK+RV
|  | SB2/D6/T3 | ASK for alternate product that can be used | VM
|  | SB2/D6/T4 | Validate order | TG+RV
| Mark item As out of Stock | SB2/D7/T1 | Check the database for out of stock items | PC
|  | SB2/D7/T2 | if item out of stock mark it | SK
|  | SB2/D7/T3 | Update the database for out of stock items | VM+RV
|  | SB2/D7/T4 | Show the user about such items | TG+RP
| Add new item | SB2/D8/T1 | Add new items to database | PC
|  | SB2/D8/T2 | Update the user about the same | VM+RV
|  | SB2/D8/T3 | List the items price | TG+RP
|  | SB2/D8/T4 | VMecifications about items | TG+VM+PC+SK

## SB Hours 02
sprint Backlog 2
S. No. | User Story | Tarms | T M | Status | Days Left in sprint
Hours
EPIC-III : Final Deployment Of Project
1 | Order Deatil | Check order detail
Location of order
Is the order Valid
2 | Order Accepted | Get the request
Check if item available
Revert back with response
Finalise the order
3 | To see customer record | See the Customer info
Order placed by customer
No. of total customers
No of orders placed
4 | Items Availability | When order is placed a request is generated
Generated request comes to owner portal
Validating the order if items available
If item not available tell the user
When available flag the user about availability
5 | Deliver Men Details | Know delivermen background details
Gives credentials to delivery men
Items he/she need to deliver
Address where they need to deliver
6 | Contact customer for non-availability of products | When order is placed check for product
if item not available tell the user
Arm for alternate product that can be used
Validate order
7 | Mark item As out of Stock | Check the database for out of stock items
if item out of stock mark it
Update the database for out of stock items
Show the user about such items
8 | Add new item | Add new items to database
Update the user about the same
List the items price
specifications about items
Verified By:
(Product Owner)

## SB BD Ch02
spring Backlog 02 burn down chart
Date | Planned Total Tarm | Actual Uncompleted Tarm
2017-09-26 | 46 | 46 | Tarms
2017-09-28 | 41
2017-10-02 | 26
2017-10-05 | 17
2017-10-07 | 7
2017-10-09 | 0
0
Days

## SprintBacklog 3
spRINT BACKLOG 3
US ID | USER STORY | TArm ID | TArmS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TArm COMPLETION
spRINT 3 - <Digital College>
| contact customer support |  | create UI to contact customer support
connect to server
send mail to owner if any issues encountered
User will receive acknowledgement number for further support
| new order placed |  | create UI for available items
select item from the menu and place them in the cart
select subscription if required
apply offer if any available
connect to server
Place order send user to payment gateway
| add item to cart |  | Create UI for every individual item
Select the quantity of particular item
Confirm to send to cart
| delete item from cart |  | code the implementation of delete button
confirmation to delete the item
Show updated changes
Undo the delete changes
| subscribe an item |  | Create subscription UI
select interval to repeat the order
special instructions for order
Show average cost of subscription
| view details |  | Create individual page for each product
See the availabilty of that item
estimated delivery of that item
Can add the item to cart
| see available offers |  | Create UI to show available offers
Fetch the available offers from server
Choose a particular offer
Apply offer if any available
| special instructions |  | Create block for special instructions
confirm to apply this instruction
Send instructions to the server
Acknowledge the user
| add address |  | Create UI for add address
Choose area
Type proper adress
Verify address
| save address |  | Create UI for saved address
Add addrees
Click on save address button
| view paymant method |  | Create UI for Payment method
Click on payment method
View available payment method
Choose available payment method
| place order |  | Select payment method
choose address
Place order
| order confirmed |  | Create UI for order confirmed
Connect to server
Send acknowledge to user
Update records

## SB Hours 03
sprint Backlog 3
S. No. | User Story | Tarms | T M | Status | Days Left in sprint
Hours
EPIC-III : Final Deployment Of Project
1 | contact customer support | create UI to contact customer support
connect to server
send mail to owner if any issues encountered
User will receive acknowledgement number for further support
2 | new order placed | create UI for available items
select item from the menu and place them in the cart
select subscription if required
apply offer if any available
connect to server
Place order send user to payment gateway
3 | add item to cart | Create UI for every individual item
Select the quantity of particular item
Confirm to send to cart
4 | delete item from cart | code the implementation of delete button
confirmation to delete the item
Show updated changes
Undo the delete changes
5 | subscribe an item | Create subscription UI
select interval to repeat the order
special instructions for order
Show average cost of subscription
6 | view details | Create individual page for each product
See the availabilty of that item
estimated delivery of that item
Can add the item to cart
7 | see available offers | Create UI to show available offers
Fetch the available offers from server
Choose a particular offer
Apply offer if any available
8 | special instructions | Create block for special instructions
confirm to apply this instruction
Send instructions to the server
Acknowledge the user
9 | add address | Create UI for add address
Choose area
Type proper adress
Verify address
10 | save address | Create UI for saved address
Add addrees
Click on save address button
11 | view paymant method | Create UI for Payment method
Click on payment method
View available payment method
Choose available payment method
12 | place order | Select payment method
choose address
Place order
13 | order confirmed | Create UI for order confirmed
Connect to server
Send acknowledge to user
Update records
Verified By:
(Product Owner)

## SB BD Ch03
spring backlog 3 Burnt Down chart
Date | Planned Total Tarm | Actual Uncompleted Tarm
2018-10-11 | 51 | 51 | Tarms
2018-10-15 | 31
2018-10-17 | 24
2018-10-20 | 16
2018-10-22 | 8
2018-10-23 | 0
0
Days

## SprintBacklog 4
spRINT BACKLOG 4
US ID | USER STORY | TArm ID | TArmS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TArm COMPLETION
spRINT 4 - <Digital College>

## SB Hours 04
sprint Backlog 4
S. No. | User Story | Tarms | T M | Status | Days Left in sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Tarm | Actual Uncompleted Tarm
2019-01-10 |  |  | Tarms
2019-01-11
2019-01-12
2019-01-13
2019-01-14
2019-01-15
0
Days